## Infomation
SWP391 - Group 5
I. Members |  |  |  | II. Project's information
# | Full name | Student ID | Total LOC | # | Field | Value
1 | Nguyễn Đức Thịnh ( L ) | HE186687 |  | 1 | Project Name
2 | Lê Hồng Phong | HE186973 |  | 2 | Repository | Git hub
3 | Triệu Hoàng Sơn | HE186811 |  | 3 | SRS Document
4 | Đỗ Trung Phúc | HE186871 |  | 4 | SDS Document
5 | Nguyễn Hoàng Vương | HE186691 |  | 5 | Issues Report
|  |  |  | 6 | Final Release Document

## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Screen/Function Name1 | Feature Name1 | Admin, Manager | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Updated | iter1 | iter2
2 | Screen/Function Name2 | Feature Name2 | Admin | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | Done | iter2 | none
3 | Screen/Function Name3 | Feature Name2 | Admin | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | Doing | iter3 | none
4 | User Login | Common | User | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Tử Vinh | To Do | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Title | Description | Screen/Function | In Charge | Iteration | Status | SRS | SDS | Notes
1 | Context diagram | Write context diagram |  | Nguyễn Đức Thịnh | Iteration 1 | Doing
2 | Template home | Find and edit form template |  | Lê Hồng Phong | Iteration 1 | Done
3 | Template client side | Find and edit form template |  | Triệu Hoàng Sơn, Nguyễn Hoàng Vương | Iteration 1 | Done
4 | Template admin side | Find and edit form template |  | Đỗ Trung Phúc | Iteration 1 | Done
5
Note on H5: KienNT: The name of section in the SRS (software requirement specification) document
Note on I5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document